## Intro
XYZ is a medical insurance clearing house. A medical insurance clearinghouse receives healthcare claims from providers, such as hospitals, clinics, and physician offices, validates and converts claim data into standardized formats, and transmits claims to insurance payers. It also handles eligibility inquiries, claim acknowledgments, payment information, and electronic remittance advice.
A clearinghouse must manage risks involving HIPAA compliance, electronic data interchange (EDI), cybersecurity, system availability, data accuracy, third-party vendors, and business continuity.
Scope and Scoring
Claims processing applications, payer connections, provider portals, databases, cloud infrastructure, employees, contractors, and third-party service providers.
The following scoring matrix is used in this risk register
| Element | Scale
| Likelihood (L) | 1 = Rare; 2 = Unlikely; 3 = Possible; 4 = Likely; 5 = Almost certain
| Impact (I) | 1 = Minimal; 2 = Minor; 3 = Moderate; 4 = Major; 5 = Severe
| Risk score | Likelihood × Impact
| Risk rating | 1–4 = Low; 5–9 = Moderate; 10–16 = High; 17–25 = Critical
| Inherent risk | Risk before considering existing controls
| Residual risk | Risk remaining after existing controls

## Risk Register
ID | Category | Risk Scenario | Inherent Risk Score (LxI) | Existing Control | Residual Risk Score(LxI) | Mitigation | Risk Owner
R01 | Cybersecurity | PHI data breach-Ransomware or Hacking exposes PHI and halts claim processing | (L4xI5) 20 - Critical | Daily backups, Periodic patch | (L3xI5) 15 - High | Apply MFA, Network Segmentation | CISO
R02 | Operations | EDI claim transmission errors-Invalid or incorrectly mapped 837 claim data results in rejected, delayed or incorrectly processed claims | (L4xI4) 16 - High | Pre-production testing, Payer specific business rules, Change management control, Automated monitoring of 999 and 277CA acknowledgements | (L2xI5) 10 - High | Automated EDI Validation, Periodic mapping review, Automated alerts for abnormal rejection rates | Operations Manager
R03 | Operations | System Outage-Major platfor outage interrupts claim, eligibility and remittance flows | (L3xI5) 15 - High | Infrastructure monitoring, Backup and recovery, Disaster Recovery Plan, Business Continuity Plan, Sceduled maintenance management | (L2xI5) 10 - High | Redundant Infrastructure, Automated alerts and notifications | Operations Manager
R04 | Compliance | HIPAA compliance failure-Organization's risk analysis omits systems or dataflows, leaving important vulnerabilities unidentified and remediation undocumented | (L3xI5) 15 - High | Annual security risk analysis, Maintain evidence | (L2xI5) 10 - High | Quarterly access reviews, Workforce training | Compliance Officer
R05 | Cybersecurity | Insider Threat-An employee or contractor improperly accesses, discloses or exports patient or claim data | (L3xI4) 12 - High | Role based access, User behavior analytics, Background checks | (L2xI4) 8 - Moderate | Least privilege access, Periodic reviews of access, Workforce training | IAM Manager
R06 | Cybersecurity | Third party vendor risk- A cloud service or subcontractor incident exposes ePHI or interrupts crtical clearing house service | (L2xI5) 10 - High | Vendor due diligence, BAAs (Business Associate Agreements), Exit strategy | (L1xI5) 5 - Moderate | Periodic assessment of vendor and associates | Vendor Risk Manager
R07 | Fraud | Fraudulent Claim Activity- Compromised customer credentials are used to submit fraudulent claims | (L2xI3) 6 - Moderate | Anomaly detection, API key rotation | (L1xI4) 4 - Low | Apply MFA, periodic password change | Fraud/ Risk Manager